## Board
SQDIP board
One row per letter, one column per day. Type the day's value: it turns green when the target is met, red when it is missed.
Team / area | Final assembly, shift A
Month (first day) | 2026-10-01
Letter | Measure | Target | Green when | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Met | Missed | Streak
S | Safety: Recordables and near misses | 0 | Lower is better | 1: 0; 2: 0; 3: 0; 4: 0; 5: 1; 6: 0; 7: 0; 8: 0; 9: 0; 10: 0; 11: 0; 12: 0
Q | Quality: First pass yield, % | 97 | Higher is better | 1: 98.2; 2: 97.6; 3: 96.4; 4: 98.9; 5: 97.3; 6: 97.8; 7: 98.4; 8: 99; 9: 97.5; 10: 98.1; 11: 96.1; 12: 96.8
D | Delivery: Units vs shift plan | 228 | Higher is better | 1: 229; 2: 214; 3: 220; 4: 231; 5: 228; 6: 230; 7: 226; 8: 233; 9: 228; 10: 219; 11: 229; 12: 232
I | Inventory: WIP ahead of the cell, pcs | 900 | Lower is better | 1: 610; 2: 700; 3: 820; 4: 760; 5: 690; 6: 880; 7: 850; 8: 960; 9: 930; 10: 720; 11: 640; 12: 600
P | Productivity: Units per labor hour | 2.5 | Higher is better | 1: 2.6; 2: 2.5; 3: 2.3; 4: 2.7; 5: 2.6; 6: 2.5; 7: 2.6; 8: 2.8; 9: 2.5; 10: 2.6; 11: 2.7; 12: 2.5
Higher is better
Yellow cells are yours to edit. Met, Missed and Streak calculate themselves: Streak counts met days since the last missed one, empty days skipped.
Build the same board online, print it or share it as a link: |  |  |  | 4: https://www.teamguru.com/tools/sqdip-board
How to run the 10-minute board meeting: |  |  |  | 4: https://www.teamguru.com/guides/sqdip

## Actions
Actions
Every red square gets a row: what is being done, who owns it, by when. Open actions past their due date turn red.
Letter | Issue and action | Owner | Due date | Status
Q | Bent connector pins: 8D opened with the supplier | K. Malik | 2026-10-20 | In progress
D | Replace the worn feeder rail on line 2 | M. Ortiz | 2026-10-19 | In progress
I | Pull system check: WIP above 900 two days running | J. Rivera | 2026-10-24 | Open

## How to use
How to use this SQDIP board
1 | Board sheet: set your team or area and the first day of the month in the yellow cells at the top.
2 | Keep S, Q, D, I, P or type your own letters. One measure per letter that the shift can move.
3 | Set each target and choose Higher is better or Lower is better. Green means the target was met.
4 | Delete the example values. Every morning, type yesterday's value under its day: it turns green or red.
5 | Every red gets a row on the Actions sheet: what is being done, who owns it, by when.
6 | Next month: save a copy, clear the daily values and change the month. Met, missed and streak recalculate.
Red is not the failure. A red with no action is. The full method, with the 10-minute agenda:
https://www.teamguru.com/guides/sqdip
Several teams, a tier 2 view, actions with owners and reminders: the same board runs in TeamGuru, fed from your metric dashboards.
https://www.teamguru.com/tools/sqdip-board